## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2017-03-07
Project Name: | SpotaGuide | [5 empty] | Project Status: | G
Project Description: | Travellers who are unfamiliar with a city can acquire or create a personalized itinerary ahead of their visit. Locals will earn money by building, managing, and facilitating unique tours of the city’s best food and entertainment.
Customer | Tourists
Project Core Team: | Philip Tocci, Kevin Vong, Anthony Vu, Brian Wallace
Next Milestone: | Start working on the prototype.
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2017-04-12 | Testing | R | 2017-03-28
Design | G | 2017-04-12 | Installation | R | 2017-04-12
Construction | G | 2017-04-12
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Our finished project website can be seen at - http://community.mis.temple.edu/spotaguide/. We also have an idea/blueprint of what we want our prototype to have and do.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Charter | G | Revision |  | 2017-01-31 | 2017-02-07 |  | 2017-02-21 | 2017-02-21
Project Website | G | Development |  | 2017-02-07 | 2017-02-14 |  | 2017-02-28 | 2017-02-28
Prototype | Y | Design |  | 2017-03-04 | 2017-03-04 |  | 2017-03-11
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Prototype Blueprint |  | Y | We are currently in the progress of mapping out what we want our prototype to look like. There are a lot of functions we want to have but we have to decide if we really need it or not. |  |  |  | All
Planned Accomplishments
We want to start working on our prototype next week and also start thinking about other deliverables for the project. We will also meet with Tony to discuss the progress of our project.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.