## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2017-04-25
Project Name: | SpotaGuide | [5 empty] | Project Status: | G
Project Description: | Travellers who are unfamiliar with a city can acquire or create a personalized itinerary ahead of their visit. Locals will earn money by building, managing, and facilitating unique tours of the city’s best food and entertainment.
Customer | Tourists
Project Core Team: | Philip Tocci, Kevin Vong, Anthony Vu, Brian Wallace
Next Milestone: | Hand in all project deliverables.
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2017-04-12 | Testing | G | 2017-03-28
Design | G | 2017-04-12 | Installation | G | 2017-04-12
Construction | G | 2017-04-12
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
We have completed our protoype as well as all of our project documentation.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Charter | G | Revision |  | 2017-01-31 | 2017-02-07 |  | 2017-02-21 | 2017-02-21
Project Website | G | Development |  | 2017-02-07 | 2017-02-14 |  | 2017-02-28 | 2017-02-28
Prototype | G | Design |  | 2017-03-04 | 2017-03-04 |  | 2017-03-11 | 2017-04-18
Competitor Analysis | G | Revision |  | 2017-03-11 | 2017-03-11 |  | 2017-03-20 | 2017-03-20
Systems Architecture | G | Revision |  | 2017-03-14 | 2017-03-14 |  | 2017-03-30 | 2017-03-21
Financials | G | Revision |  | 2017-04-07 | 2017-04-07 |  | 2017-04-18 | 2018-04-17
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Prototype |  | Y | The prototype is finished and has everything that we want it to have. |  |  |  | All
Financials |  | Y | We have fixed our financials and are not profiting by year 3.
Planned Accomplishments
Project completed! We are now looking to hand in all of our final deliverables.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.