## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-02-22
Project Name: | Survey Dinosaur (place holder?) | [5 empty] | Project Status: | Y
Project Description: | Online surveys are currently time consuming and boring. Many surveys also screen you out half way through. We are aiming to create an application that makes surveys easy and hassle free to complete as well as be profitable to our company.
Customer | Tony Messina
Project Core Team: | Tom Couser, Nick Hurtado, Donjie Wang, Khaleque
Next Milestone: | Finalization of application analysis
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Planning | G | 2016-02-16 | Testing | G | 2016-03-27 | Analysis | Y | 2016-03-01
Design | G | 2016-03-10 | Installation | G | 2016-04-20
Construction | G | 2016-03-25
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Determined application audience
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Application Audience research | G | Analysis |  | 2016-02-16 | 2016-02-16 | Determined the audience we want to target, further analysis in progress, will be able to complete by deadline | 2016-03-01 | 2016-03-01
Application Viability Research | Y | Analysis |  | 2016-02-16 | 2016-02-16 | Questions need to be addressed regarding potential saftey risks of using application in the car, discussing again next meeting | 2016-03-01 | 2016-03-01
Application Profitability Research | Y | Analysis |  | 2016-02-16 | 2016-02-16 | Starting to look into profitability of the survey application, very little progress made this week | 2016-03-01 | 2016-03-01
Application Name Decision | Y | Analysis |  | 2016-02-16 | 2016-02-16 | Survey Dinosaur was promoted by one of our groupmates, viablity of name still being debated | 2016-03-01 | 2016-03-01
Application Features | Y | Analysis |  | 2016-02-16 | 2016-02-16 | Discussing key features application needs to have, this activity was added this week | 2016-03-01 | 2016-03-01
Application Layout | G | Design |  | 2016-03-01 | 2016-03-01 | Have began discussions regarding application layout | 2016-03-10 | 2016-03-10
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Application Viability Research |  | Y | Questions need to be addressed regarding potential saftey risks of using application in the car, discussing again next meeting |  |  |  | Nick
Application Name Decision |  | Y | Survey Dinosaur was promoted by one of our groupmates, viablity of name still being debated |  |  |  | Nick
Application Profitability Research |  | Y | Starting to look into profitability of the survey application, very little progress made this week |  |  |  | Nick
Application Features |  | Y | Discussing key features application needs to have, this activity was added this week
Planned Accomplishments
Next week we will need to have our analysis completed and start working on the base design of the project.
Note on B45: Key Issues are issues that need your CM Director-level understanding and awareness.