## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-02-08
Project Name: | Survey Application (Place Holder Name) | [5 empty] | Project Status: | Y
Project Description: | Online surveys are currently time consuming and boring. Many surveys also screen you out half way through. We are aiming to create an application that makes surveys easy and hassle free to complete as well as be profitable to our company.
Customer | Tony Messina
Project Core Team: | Tom Couser, Nick Hurtado, Donjie Wang, Khaleque
Next Milestone: | Finalization of Project Ideas
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Planning | Y | 2016-02-16 | Testing | G | 2016-03-27 | Analysis | Y | 2016-03-01
Design | G | 2016-03-10 | Installation | G | 2016-04-20
Construction | G | 2016-03-25
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
None
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Application Research | Y | Planning |  | 2016-02-01 | 2016-02-01 | Still deciding if our application is the one we want to stick with | 2016-02-16 | 2016-02-16
Application Audience research | Y | Analysis |  | 2016-02-16 | 2016-02-16 | Waiting on application decision | 2016-03-01 | 2016-03-01
Application Viability Research | Y | Analysis |  | 2016-02-16 | 2016-02-16 | Waiting on application decision | 2016-03-01 | 2016-03-01
Application Profitability Research | Y | Analysis |  | 2016-02-16 | 2016-02-16 | Waiting on application decision | 2016-03-01 | 2016-03-01
Application Name Decision | Y | Analysis |  | 2016-02-16 | 2016-02-16 | Waiting on application decision | 2016-03-01 | 2016-03-01
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Deciding on Application |  | Y | Still deciding if our application is the one we want to stick with |  |  |  | All
Planned Accomplishments
Next week we will need to have our application decided on and have already worked on many parts of the application analysis
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.