## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-03-14
Project Name: | Survey Dinosaur | [5 empty] | Project Status: | G
Project Description: | Online surveys are currently time consuming and boring. Many surveys also screen you out half way through. We are aiming to create an application that makes surveys easy and hassle free to complete as well as be profitable to our company.
Customer | Tony Messina
Project Core Team: | Tom Couser, Nick Hurtado, Donjie Wang, Khaleque Ismail
Next Milestone: | Construction of basic prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Planning | G | 2016-02-16 | Testing | G | 2016-03-27 | Analysis | G | 2016-03-01
Design | G | 2016-03-10 | Installation | G | 2016-04-20
Construction | G | 2016-03-25
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Basic prototype - survey screens | G | Construction |  | 2016-03-14 | 2016-03-14 | Creation of basic survey screens in JIM | 2016-03-21 | 2016-03-21
Basic prototype -profile screens | G | Construction |  | 2016-03-14 | 2016-03-14 | Creation of basic profile screens in JIM | 2016-03-21 | 2016-03-21
Application Layout | G | Design |  | 2016-03-01 | 2016-03-01 | Application layout has been determined | 2016-03-10 | 2016-03-10
Application Color Scheme | G | Design |  | 2016-03-01 | 2016-03-01 | Color scheme has been determined | 2016-03-10 | 2016-03-10
Basic prototype -social screens | G | Construction |  | 2016-03-14 | 2016-03-14 | Creation of basic social screens in JIM | 2016-03-21 | 2016-03-21
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Application Layout |  | G | Application layout has been deterimed |  |  |  | Tom
Creation of basic prototype |  | G | Beginning to create the base of the prototype |  |  |  | Tom, Khaleque, Dongjie
Planned Accomplishments
Next week we will need to have the basic prototype created
Note on B41: Key Issues are issues that need your CM Director-level understanding and awareness.