## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-03-21
Project Name: | Survey Dinosaur | [5 empty] | Project Status: | G
Project Description: | Online surveys are currently time consuming and boring. Many surveys also screen you out half way through. We are aiming to create an application that makes surveys easy and hassle free to complete as well as be profitable to our company.
Customer | Tony Messina
Project Core Team: | Tom Couser, Nick Hurtado, Donjie Wang, Khaleque Ismail
Next Milestone: | Finalization of prototype and use cases
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Planning | G | 2016-02-16 | Testing | G | 2016-03-27 | Analysis | G | 2016-03-01
Design | G | 2016-03-10 | Installation | G | 2016-04-20
Construction | G | 2016-03-25
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Created the basic prototype
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Basic prototype - survey screens | G | Construction |  | 2016-03-14 | 2016-03-14 | Creation of basic survey screens in JIM | 2016-03-21 | 2016-03-21
Basic prototype -profile screens | G | Construction |  | 2016-03-14 | 2016-03-14 | Creation of basic profile screens in JIM | 2016-03-21 | 2016-03-21
Basic prototype -social screens | G | Construction |  | 2016-03-14 | 2016-03-14 | Creation of basic social screens in JIM | 2016-03-21 | 2016-03-21
Apply color scheme to prototype | G | Construction |  | 2016-03-21 | 2016-03-21 | Apply color scheme to prototype | 2016-03-28
Link protoype pages together and make design uniform | G | Construction |  | 2016-03-21 | 2016-03-21 | Link all prototype pages together and make all design elements uniform | 2016-03-28
Create use cases | G | Construction |  | 2016-03-21 | 2016-03-21 | creation of use cases | 2016-04-04
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Creation of basic prototype |  | G | Basic prototype created |  |  |  | Tom, Khaleque, Dongjie
Create use cases |  | G | Need to talk about all possible use cases |  |  |  | Nick
Planned Accomplishments
Next week we will finalize the protype and make good progress on the use cases
Note on B42: Key Issues are issues that need your CM Director-level understanding and awareness.