## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-03-07
Project Name: | Survey Dinosaur | [5 empty] | Project Status: | G
Project Description: | Online surveys are currently time consuming and boring. Many surveys also screen you out half way through. We are aiming to create an application that makes surveys easy and hassle free to complete as well as be profitable to our company.
Customer | Tony Messina
Project Core Team: | Tom Couser, Nick Hurtado, Donjie Wang, Khaleque Ismail
Next Milestone: | Finalization of application design
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Planning | G | 2016-02-16 | Testing | G | 2016-03-27 | Analysis | G | 2016-03-01
Design | G | 2016-03-10 | Installation | G | 2016-04-20
Construction | G | 2016-03-25
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Determined project viability and profitablity
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Application Name Decision | G | Analysis |  | 2016-02-16 | 2016-02-16 | Survey Dinosaur was promoted by one of our groupmates, viablity of the name has been debated and we have decided to keep it. | 2016-03-01 | 2016-03-01
Application Features | G | Analysis |  | 2016-02-16 | 2016-02-16 | Determined the key features needed in the application | 2016-03-01 | 2016-03-02
Application Layout | G | Design |  | 2016-03-01 | 2016-03-01 | Application layout is still be debated but is nearing completion | 2016-03-10
Application Color Scheme | G | Design |  | 2016-03-01 | 2016-03-01 | Debating the color scheme or application should have | 2016-03-10
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Application Name Decision |  | G | Survey Dinosaur was promoted by one of our groupmates, viablity of the name has been debated and we have decided to keep it. |  |  |  | Nick
Application Features |  | G | Determined the key features needed in the application |  |  |  | Tom
Application Layout |  | G | Discussing what the overall layout of the application should be |  |  |  | Tom
Planned Accomplishments
Next week we will need to have the basic design of our application completed.
Note on B41: Key Issues are issues that need your CM Director-level understanding and awareness.