## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-04-11
Project Name: | Survey Dinosaur | [5 empty] | Project Status: | G
Project Description: | Online surveys are currently time consuming and boring. Many surveys also screen you out half way through. We are aiming to create an application that makes surveys easy and hassle free to complete as well as be profitable to our company.
Customer | Tony Messina
Project Core Team: | Tom Couser, Nick Hurtado, Donjie Wang, Khaleque Ismail
Next Milestone:
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Planning | G | 2016-02-16 | Testing | G | 2016-03-27 | Analysis | G | 2016-03-01
Design | G | 2016-03-10 | Installation | G | 2016-04-20
Construction | G | 2016-03-25
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Finalized the final protoype and use cases
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Create presentation | G | Construction |  | 2016-04-04 | 2016-04-04 | Create final presentation | 2016-04-11 | 2016-04-11
Finalize all other documentation | G | Construction |  | 2016-04-04 | 2016-04-04 | Finalize other documentation like architecture , financials, etc. | 2016-04-11 | 2016-04-11
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Presentation |  | G | Created presentation. Tom, Nick, and Khaleque are presenting |  |  |  | Tom
Finalize all other documentation |  | G | Finalized all other doucmentation |  |  |  | Nick, Dongjie
Planned Accomplishments
Over the next week we will practive our presentation
Note on B38: Key Issues are issues that need your CM Director-level understanding and awareness.