## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-04-04
Project Name: | Survey Dinosaur | [5 empty] | Project Status: | G
Project Description: | Online surveys are currently time consuming and boring. Many surveys also screen you out half way through. We are aiming to create an application that makes surveys easy and hassle free to complete as well as be profitable to our company.
Customer | Tony Messina
Project Core Team: | Tom Couser, Nick Hurtado, Donjie Wang, Khaleque Ismail
Next Milestone: | Finalization of presentation and documentation
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Planning | G | 2016-02-16 | Testing | G | 2016-03-27 | Analysis | G | 2016-03-01
Design | G | 2016-03-10 | Installation | G | 2016-04-20
Construction | G | 2016-03-25
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Finalized the final protoype and use cases
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Finalized prototype - survey screens | G | Construction |  | 2016-03-28 | 2016-03-28 | Creation of final survey screens in JIM | 2016-04-04 | 2016-04-04
Finalized prototype - social screens | G | Construction |  | 2016-03-28 | 2016-03-28 | Creation of basic social screens in JIM | 2016-04-04 | 2016-04-04
Finalized prototype - profile screens | G | Construction |  | 2016-03-28 | 2016-03-28 | Creation of final profile screens in JIM | 2016-04-04 | 2016-04-04
Create use cases | G | Construction |  | 2016-03-21 | 2016-03-21 | create use cases | 2016-04-04 | 2016-04-04
Create presentation | G | Construction |  | 2016-04-04 | 2016-04-04 | Create final presentation | 2016-04-11 | 2016-04-11
Finalize all other documentation | G | Construction |  | 2016-04-04 | 2016-04-04 | Finalize other documentation like architecture , financials, etc. | 2016-04-11 | 2016-04-11
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Create final protoype |  | G | Finalized prototype has been finished |  |  |  | Tom
Create use cases |  | G | Nick has completed the use cases |  |  |  | Nick
Presentation |  | G | Creating presentation as a team and determining presenters |  |  |  | Tom
Finalize all other documentation |  | G | Finalize other documentation like architecture , financials, etc. |  |  |  | Nick, Dongjie
Planned Accomplishments
Next week we will finalize our entire project
Note on B42: Key Issues are issues that need your CM Director-level understanding and awareness.