## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2017-11-06
Project Name: | TUStudy | [5 empty] | Project Status: | G | G | Good/Completed
Project Description: | An easy-to-use app for students to locate and utilize available computers, breakout rooms, writing & tutorial appointments at Temple University. | [7 empty] | Y | Ongoing/Under work
[9 empty] | R | Yet to be started/initiated
Customer | Temple University
Project Core Team: | Project Manager: BS Srinath Amruth Business Analyst: Glenn Diener Solutions Engineer: Jacky Wong
Next Milestone: | Delivery of Testing plan
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2017-11-06 | Testing | G | 2017-11-06
Design | G | 2017-11-06
Construction | G | 2017-11-06
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Last week we came together and talked about the design of the project and how we should divide up the work in JustInMind. The layout/GUI is still a work in progress. Neccesary information has been provided by Mentors which will help in creating a more tailor-made product.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Test plan | G | Design |  | 24th Oct |  |  | 11th Dec
Final project plan | G | Analysis |  | 24th Oct |  |  | 20th Oct
UI Mockup | G | Design |  | 24th Oct |  |  | 11th Dec
--- User login | G | Design |  | 24th Oct |  |  | 14th Nov
--- Sidebar Menu | G | Design |  | 24th Oct |  |  | 11th Dec
--- Reservation Confirmation | G | Design |  | 24th Oct |  |  | 11th Dec
--- Reservation Menu | G | Design |  | 24th Oct |  |  | 14th Nov
--- Room Res landing page | G | Design |  | 24th Oct |  |  | 20th Nov
--- Tutor Res landing page | G | Design |  | 24th Oct |  |  | 20th Nov
--- Writing Asst Res landing page | G | Design |  | 24th Oct |  |  | 20th Nov
--- Computer Res landing page | G | Design |  | 24th Oct |  |  | 20th Nov
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Time period of Reservation |  | G | To consult with Tech Director of Tech Center - To be 1 hour for adequate time |  |  |  | Amruth
Allowing only 1 reservation at a time |  | G | Algorithm to be research and implemented |  |  |  | Jacky
Planned Accomplishments
1. The front facing page of the app has been constructed. 2. Resource options have been stated out in the following page. 3. Landing pages of each resource have been created.
Note on B48: Key Issues are issues that need your CM Director-level understanding and awareness.