## Status Summary
Project Dashboard
| Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2017-03-29
| Project Name: | VisRecs | [5 empty] | Project Status: | R
| Project Description: | There is currently a large amount of unstructured data hidden within images, videos, gifs etc. being uploaded to social media/the internet. Metadata can be very ambiguous, making it difficult to drive decision making. By using Watsons visual recognition technology, we can begin to harness this data and structure it into meaningful ideas—using user uploaded media to recommend restaurants, shopping, museums and other attractions within Philadelphia. Our project takes place in multiple phases, of which we are demonstrating phase two. Phase one includes training and building a Philadelphia corpus for Watson. Phase two involves building the application to allow user submissions into the corpus and to generate and push recommendations to users based on inputs. Phase three would be marketing this rich visual content to interested parties.
| Customer | Those who live in or are visiting Philadelphia
| Project Core Team: | Dominick Falco, Alex Korjeski, Alex Meyer, Louisa Carleton
| Next Milestone: | Prototype Creation
Phase Status
|  | Status | Plan |  | Status | Plan |  | Status | Date
| Analysis | Y |  | Testing | Y
| Design | Y |  | Installation | R
| Construction | Y
| Leading Indicators | Status |  |  | Status |  |  | Status
| On-Time | R | On-Budget |  | G | Delivery to Scope |  | R
Major Accomplishments/Decisions
We have a semi-feasbile idea that we need to change in order to move forward with the project. We changed from our initial plan due to similarity with several existing applications.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
[5 empty] | START |  |  | END
| Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
| Project Proposal | Y | Planning
| Project Charter | Y | Planning
| UI Mockup | Y | Design |  |  |  | Screens and features are dilineated on paper but not yet built in JIM.
| Quaility Mgmt | Y | Execution
| Community Site | Y | Execution |  |  |  | Our website is established and content is being added/updated.
| Presentation Slides | Y | Design |  |  |  | In a meeting today we began a first draft for our slide deck.
Customer Profiles | Customer Profiles | Y | Execution
| Revision of Financials | R | Execution
Key Issues
| Description |  | Status | Resolution/Update |  |  |  | Owner
| Project Charter Description |  | Y | We will revise the description part of project charter so that it is more specific |  |  |  | Alex
Planned Accomplishments
Before our next meeting, we plan on having solid designs for the UI built in JIM. We also want to revise our project charter to further specify anything that could be broad and come up with three use cases to build upon for our presentation.
Note on B44: Key Issues are issues that need your CM Director-level understanding and awareness.