## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2018-01-30
Project Name: | Warehouse Wizard | [5 empty] | Project Status: | Y
Project Description: | QVC has recently suffered from low warehouse utilization which leads to longer delivery time, resulting in lower sales than expected. In order to improve its warehouses utilization, the company has to figure out which warehouses need to be used and which kinds of products each warehouse should primarily store since QVC, on the other hand, has plenty of warehouses left unused throughout the US.
Customer | The General Public
Project Core Team: | Kelly Conger, Ryan Gibbons, Liwei Yi, Jiawei Huang
Next Milestone: | Delivery of Testing plan
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2018-02-13 | Testing | Y | 2018-04-01
Design | Y | 2018-02-15 | Installation | Y | 2018-04-15
Construction | Y | 2018-03-01
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Defined project scope. Collected needed data for analysis.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Test plan | Y | Design |  | 2018-02-01 | 2018-02-01 |  | 2018-02-15 | 2018-02-15
Final project plan | Y | Analysis |  | 2018-03-01 | 2018-03-01 | Scope issues | 2018-03-01 | 2018-03-01
UI Mockup | Y | Design
--- User login | Y | Design |  | 2018-03-01 | 2018-03-01 |  | 2018-03-01 | 2018-03-01
--- Account maintenance | Y | Design |  | 2018-03-02 | 2018-03-02 |  | 2018-03-02 | 2018-03-02
--- Catalog maintenance | Y | Design |  | 2018-03-03 | 2018-03-03 |  | 2018-03-03 | 2018-03-03
--- Browse catalog | Y | Design |  | 2018-03-04 | 2018-03-04 |  | 2018-03-04 | 2018-03-04
--- Add to shopping cart | Y | Design |  | 2018-03-05 | 2018-03-05 |  | 2018-03-05 | 2018-03-05
etc. . .
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Planned Accomplishments
Jiawei will be doing his analysis for further use.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.