## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2018-04-03
Project Name: | Warehouse Wizard | [5 empty] | Project Status: | G
Project Description: | QVC has recently suffered from low warehouse utilization which leads to longer delivery time, resulting in lower sales than expected. In order to improve its warehouses utilization, the company has to figure out which warehouses need to be used and which kinds of products each warehouse should primarily store since QVC, on the other hand, has plenty of warehouses left unused throughout the US.
Customer | The General Public
Project Core Team: | Kelly Conger, Ryan Gibbons, Liwei Yi, Jiawei Huang
Next Milestone: | Create functional prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Planning | G | 2018-01-22 | Construction | G | 2018-03-19
Analysis | G | 2018-02-05 | Testing | G | 2018-04-02
Design | G | 2018-02-12 | Installation | G | 2018-04-09
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
The team currently accomplished: 1) We updated the data model 2) We updated the process model 3) We updated the system architecture 4) We updated our deck 5) We updated prototype 6) We finished prototype installation in advance. Along with these accomplishments, we had our weekly meeting, and discussed and updated our project scope.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Initial planning | G | Design |  | 2018-01-23 | 2018-01-30 |  | 2018-01-23 | 2018-01-30
Final project plan | G | Analysis |  | 2018-02-06 | 2018-02-20 |  | 2018-02-06 | 2018-02-20
Prototype design | G | Design
--- User login | G | Design |  | 2018-02-20 | 2018-02-20 |  | 2018-02-20 | 2018-02-20
--- Home page | G | Design |  | 2018-02-25 | 2018-02-25 |  | 2018-02-25 | 2018-02-25
--- Sales input | G | Design |  | 2018-02-27 | 2018-02-27 |  | 2018-02-27 | 2018-02-27
--- Implementation | G | Design |  | 2018-03-13 | 2018-03-13 |  | 2018-03-13 | 2018-03-13
--- Manual Modification | G | Design |  | 2018-03-18 | 2018-03-18 |  | 2018-03-18 | 2018-03-18
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Hard to find a time available for everyone to meet |  | G | We will schedule next meeting as soon as possible to avoid late time conflict |  |  |  | Everyone
Justinmind inexperience |  | Y | Team members can teach each other, and watch online tutorials to learn new functionality |  |  |  | Ryan
Planned Accomplishments
Meet with mentor and discuss how can we further improve our business case. Prepare for the final presentation.
Note on B50: Key Issues are issues that need your CM Director-level understanding and awareness.