## Copy of Status Summary Update 3
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2017-03-30
Project Name: | WorkFit | [5 empty] | Project Status: | G
Project Description: | Organizations across the world are faced with unhealthy and unproductive employees more commonly than ever before. These lethargic workers, who cannot even touch their toes, lead to decreased productivity as well as increased depression. In order to address the balance of work and activity in the workplace we are proposing a new application for a healthier workplace. Utilizing geolocation and healthy goal suggestions, including foods and activities, employees will get a better idea of how healthy they are at work. This application will remind employees to move and eat well while also updating them on their our personal goals daily, weekly or monthly. There would need to be a buy in for the company to realize that if this application is used there would be a decrease in health insurance cost for the company and individuals. Features: - Personal daily, weekly, monthly goals - Geolocation tracking for workout goals (walking, running, etc.) - Decreased food options in cafeteria - Connection with healthy food service to suggest options for the users - Friend location tracking to meet up and network as well as get up and move - Point system which goes to rewards from the company - Compete across the company individually, in teams, or in business functions to get the most points and meet the most goals.
Customer | Companies who choose to utilize the application and individuals who choose to download the application from the app store.
Project Core Team: | Jon Kerin, Thompson Nguyen, Sara Monahan, Matt Leaver
Next Milestone: | Third Iteration of Prototype and meeting with Professor Schuff (4/6/2017) and meeting with Ben Hasan (4/12/2017)
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 1/30/2017 - 4/30/2017 | Testing | R | 2017-03-28
Design | Y | 2/13/17- 4/30/2017 | Installation | R | 2017-04-30
Construction | R | 2017-03-06
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
In the past two weeks we have been doing two seperate tracks. Jon and Sara have been completing the various documents such as the scope, risk register, stakeholder register, schedule, competitor data, and financial data. We are awaiting feedback from Ben for our written deliverables in order to refine them and share them with Thompson and Matt. We are still focusing on the cost/benefit analysis and how to incorporate the individual aspect of the application to the public(awaiting Ben's advice and response). Sara and Jon are also extensively researching more financial data across the industry to get a bearing on pricing of the application and what to charge to enterprises and individuals. Thompson and Matt have been working closesly with the prototype, focusing on the design and functionality of it. Thompson is focusing on the design of the profiles within our application while Matt is working on the data and the behind the scenes functionality. Sara is still the touch point with Ben. However, Ben has not been that responsive in our emails to him regarding feedback and progression of our written deliverables. The team also refined the scope of the project and updated the project charter. Overall, the group is feeling pretty confident on our progression towards the final deliverables and the prototype progression.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Planning Project | G | Design/Analysis |  | 2017-01-30 | 2017-01-30
Business Case (Research) | Y | Analysis |  | 2017-02-13 | 2017-02-13
Prototype Planning | Y | Planning |  | 2017-02-13 | 2017-02-13
Prototype Design | R | Design |  | 2017-03-01 | 2017-03-03
R
R
R
R
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Scope Creep |  | R | Scope Creep would occur with marketing the application to employees rather than corporations |  |  |  | All
Revenue Stream |  | Y | Research phase currently; potential parterning with MilkCrate/Yelp for additional revenue |  |  |  | All
JustinMInd |  | Y | Software issues regarding saving and usage of prior prototype |  |  |  | Matt and Thompson
Planned Accomplishments
A third iteration of the prototype with functionality and profile design; outline personnas in the prototype in even more detail. A refined copy of the PowerPoint presentation will be completed by the end of the week; supported with financial data, future design iterations, and deadlines for deliverables/prototype especially. The group needs to keep refining our scope, charter, and financial documents; we are worried that we are missing some hidden costs within our prototype/project and will confirm with Ben, our mentor. Our first meeting with Professor Schuff should allow us to consolidate our revenue stream and prototyping design/idea (4/6/2017)
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.

## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2017-02-16
Project Name: | WorkFit | [5 empty] | Project Status: | G
Project Description: | Organizations across the world are faced with unhealthy and unproductive employees more commonly than ever before. These lethargic workers, who cannot even touch their toes, lead to decreased productivity as well as increased depression. In order to address the balance of work and activity in the workplace we are proposing a new application for a healthier workplace. Utilizing geolocation and healthy goal suggestions, including foods and activities, employees will get a better idea of how healthy they are at work. This application will remind employees to move and eat well while also updating them on their our personal goals daily, weekly or monthly. There would need to be a buy in for the company to realize that if this application is used there would be a decrease in health insurance cost for the company and individuals. Features: - Personal daily, weekly, monthly goals - Geolocation tracking for workout goals (walking, running, etc.) - Decreased food options in cafeteria - Connection with healthy food service to suggest options for the users - Friend location tracking to meet up and network as well as get up and move - Point system which goes to rewards from the company - Compete across the company individually, in teams, or in business functions to get the most points and meet the most goals.
Customer | Companies who choose to utilize the application and individuals who choose to download the application from the app store.
Project Core Team: | Jon Kerin, Thompson Nguyen, Sara Monahan, Matt Leaver
Next Milestone: | First iteration of prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 1/30/2017 - 4/30/2017 | Testing | R | 2017-03-28
Design | Y | 2/13/17- 4/30/2017 | Installation | R | 2017-04-30
Construction | Y | 2017-03-06
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
In the past two weeks we have been doing two seperate tracks. Jon and Sara have been doing research for the final project, focuses on the competition and cost/benefit analysis. Thompson and Matt have been working closesly with the prototype, focusing on the design and functionality of it. We also have decided that Sara will be the touch point between the project mentor and the team. The team also refinded the scope of the project and updated the project charter.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Planning Project | G | Design/Analysis |  | 2017-01-30 | 2017-01-30
Business Case (Research) | Y | Analysis |  | 2017-02-13 | 2017-02-13
Prototype Planning | Y | Planning |  | 2017-02-13 | 2017-02-13
Prototype Design | R | Design |  | 2017-03-01 | 2017-03-03
R
R
R
R
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Scope Creep |  | R | Scope Creep would occur with marketing the application to employees rather than corporations |  |  |  | All
Revenue Stream |  | Y | Research phase currently; potential parterning with MilkCrate/Yelp for additional revenue |  |  |  | All
JustinMInd |  | Y | Software issues regarding saving and usage of prior prototype |  |  |  | Matt and Thompson
Planned Accomplishments
A second iteration of the prototype with functionality; outline personnas in the prototype. A refined copy of the PowerPoint presentation supported with financial data especially. We also plan to keep refining and updating our charter. We have our first meeting on March 17th with our mentor; we plan to ask basic questions about the idea and how to refine our scope even further while getting ideas about potential revenue streams.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.

## Status Summary Update 3302017
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2017-03-30
Project Name: | WorkFit | [5 empty] | Project Status: | G
Project Description: | Organizations across the world are faced with unhealthy and unproductive employees more commonly than ever before. These lethargic workers, who cannot even touch their toes, lead to decreased productivity as well as increased depression. In order to address the balance of work and activity in the workplace we are proposing a new application for a healthier workplace. Utilizing geolocation and healthy goal suggestions, including foods and activities, employees will get a better idea of how healthy they are at work. This application will remind employees to move and eat well while also updating them on their our personal goals daily, weekly or monthly. There would need to be a buy in for the company to realize that if this application is used there would be a decrease in health insurance cost for the company and individuals. Features: - Personal daily, weekly, monthly goals - Geolocation tracking for workout goals (walking, running, etc.) - Decreased food options in cafeteria - Connection with healthy food service to suggest options for the users - Friend location tracking to meet up and network as well as get up and move - Point system which goes to rewards from the company - Compete across the company individually, in teams, or in business functions to get the most points and meet the most goals.
Customer | Companies who choose to utilize the application and individuals who choose to download the application from the app store.
Project Core Team: | Jon Kerin, Thompson Nguyen, Sara Monahan, Matt Leaver
Next Milestone: | Third Iteration of Prototype and meeting with Professor Schuff (4/6/2017) and meeting with Ben Hasan (4/12/2017)
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 1/30/2017 - 4/30/2017 | Testing | R | 2017-03-28
Design | Y | 2/13/17- 4/30/2017 | Installation | R | 2017-04-30
Construction | Y | 2017-03-06
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
In the past two weeks we have been doing two seperate tracks. Jon and Sara have been completing the various documents such as the scope, risk register, stakeholder register, schedule, competitor data, and financial data. We are awaiting feedback from Ben for our written deliverables in order to refine them and share them with Thompson and Matt. We are still focusing on the cost/benefit analysis and how to incorporate the individual aspect of the application to the public(awaiting Ben's advice and response). Sara and Jon are also extensively researching more financial data across the industry to get a bearing on pricing of the application and what to charge to enterprises and individuals. Thompson and Matt have been working closesly with the prototype, focusing on the design and functionality of it. Thompson is focusing on the design of the profiles within our application while Matt is working on the data and the behind the scenes functionality. Sara is still the touch point with Ben. However, Ben has not been that responsive in our emails to him regarding feedback and progression of our written deliverables. The team also refined the scope of the project and updated the project charter. Overall, the group is feeling pretty confident on our progression towards the final deliverables and the prototype progression.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Planning Project | G | Design/Analysis |  | 2017-01-30 | 2017-01-30
Business Case (Research) | Y | Analysis |  | 2017-02-13 | 2017-02-13
Prototype Planning | Y | Planning |  | 2017-02-13 | 2017-02-13
Prototype Design | R | Design |  | 2017-03-01 | 2017-03-03
R
R
R
R
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Scope Creep |  | R | Scope Creep would occur with marketing the application to employees rather than corporations |  |  |  | All
Revenue Stream |  | Y | Research phase currently; potential parterning with MilkCrate/Yelp for additional revenue |  |  |  | All
JustinMInd |  | Y | Software issues regarding saving and usage of prior prototype |  |  |  | Matt and Thompson
Planned Accomplishments
A third iteration of the prototype with functionality and profile design; outline personnas in the prototype in even more detail. A refined copy of the PowerPoint presentation will be completed by the end of the week; supported with financial data, future design iterations, and deadlines for deliverables/prototype especially. The group needs to keep refining our scope, charter, and financial documents; we are worried that we are missing some hidden costs within our prototype/project and will confirm with Ben, our mentor. Our first meeting with Professor Schuff should allow us to consolidate our revenue stream and prototyping design/idea (4/6/2017)
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.

## Status Summary Update 41117
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2017-04-13
Project Name: | WorkFit | [5 empty] | Project Status: | G
Project Description: | Organizations across the world are faced with unhealthy and unproductive employees more commonly than ever before. These lethargic workers, who cannot even touch their toes, lead to decreased productivity as well as increased depression. In order to address the balance of work and activity in the workplace we are proposing a new application for a healthier workplace. Utilizing geolocation and healthy goal suggestions, including foods and activities, employees will get a better idea of how healthy they are at work. This application will remind employees to move and eat well while also updating them on their our personal goals daily, weekly or monthly. There would need to be a buy in for the company to realize that if this application is used there would be a decrease in health insurance cost for the company and individuals. Features: - Personal daily, weekly, monthly goals - Geolocation tracking for workout goals (walking, running, etc.) - Decreased food options in cafeteria - Connection with healthy food service to suggest options for the users - Friend location tracking to meet up and network as well as get up and move - Point system which goes to rewards from the company - Compete across the company individually, in teams, or in business functions to get the most points and meet the most goals.
Customer | Companies who choose to utilize the application and individuals who choose to download the application from the app store.
Project Core Team: | Jon Kerin, Thompson Nguyen, Sara Monahan, Matt Leaver
Next Milestone: | Fourth Iteration of the prototype, completed apppliaction site, next meeting with our project sponsor Ben Hasan (4/12/2017)
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 1/30/2017 - 4/30/2017 | Testing | Y | 2017-03-28
Design | G | 2/13/17- 4/30/2017 | Installation | R | 2017-04-30
Construction | G | 2017-03-06
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
For the past two weeks the separate tracks have continued with some overlap. Jon and Sara have continued to update and complete the documents that our team found necessary which include up to this point: scope, risk register, stakeholder register, schedule, timeline, competitor’s data, financial data, activity costs, and status reports. Ben Hasan, project sponsor, has given some feedback on the documents and we are currently working to draft more specific questions to ask Ben to address. Our main focus in the coming weeks will be to finalize all the documents and begin on the final steps of the final presentation. Extensive research continues for Jon and Sara on all the information we need for our final report, more closely focused on costs and benefits in order to drive home the value added from this application. Matt and Thompson have been diligently working to add to our final prototype. Thompson and Sara met to work out a new design for the profile pages and Thompson has been working very hard on creating and implementing those pages. Matt has continued work on the networking section of the prototype. Matt also created the team’s project site and added the documents and status reports to it. Sara has done work on the design and text that is on the project site. Sara and Jon also have gotten access to JustinMind in order to help move long the prototype as quickly as possible. Our team is still very happy with our progress and feels that we will be able to complete this application without a problem.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Planning Project | G | Design/Analysis |  | 2017-01-30 | 2017-01-30 | Complete | 2017-02-07 | 2017-02-07
Business Case (Research) | Y | Analysis |  | 2017-02-13 | 2017-02-13 | In Progress | 2017-04-11 | -
Prototype Planning | G | Planning |  | 2017-02-13 | 2017-02-13 | Complete | 2017-02-28 | 2017-03-02
Prototype Design | Y | Design |  | 2017-03-01 | 2017-03-03 | In Progress | 2017-04-18 | -
Project Site | Y | Design |  | 2017-03-30 | 2017-04-04 | In Progress | 2017-04-18 | -
R
R
R
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Scope Creep |  | R | Scope Creep would occur with marketing the application to employees rather than corporations |  |  |  | All
Revenue Stream |  | Y | Research phase currently; potential parterning with MilkCrate/Yelp for additional revenue |  |  |  | All
JustinMind |  | Y | Software issues regarding saving and usage of prior prototype |  |  |  | Matt and Thompson
Planned Accomplishments
Fourth iteration of the prototype, as close to being complete as possible with functionality and a completed personal profile, team profile, and the networking section complete. A complete copy of the final PowerPoint presentation so we can being to work on our presentation technique. The PowerPoint includes the problem, solution, competitor data, financial data, schema, data model and other documents we will fit to include. Continue working on refining the documents with help from Ben Hasan. Our second meeting with our project sponsor Ben Hasan (4/12/2017) to go over final design and continued questions about our documents. The final presentation will be on April 25th 2017.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.