## Week
WorkFIT Project Schedule
|  | Start Week | 2017-01-17
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Starting | 2017-01-17 | 2017-01-24 | 2017-01-31 | 2017-02-07 | 2017-02-14 | 2017-02-21 | 2017-02-28 | 2017-03-07 | 2017-03-14 | 2017-03-21 | 2017-03-28 | 2017-04-04 | 2017-04-11 | 2017-04-18 | Notes
| 2017-01-17 | 2017-01-24 | 2017-01-31 | 2017-02-07 | 2017-02-14 | 2017-02-21 | 2017-02-28 | 2017-03-07 | 2017-03-14 | 2017-03-21 | 2017-03-28 | 2017-04-04 | 2017-04-11 | 2017-04-18
Team Creation
Idea Creation
Phase One | 2017-01-31: Status Report #1 and Charter
Scope Document
Phase | 2017-02-07: Prototyping (see prototyping path)
Two | 2017-02-07: Research and Documentation (see documentation path)
Status Update
Status Update
Sponsor Update
Phase | 2017-03-28: Sponsor Update
Three | 2017-04-04: Final Status Update
Final Prototype
Final Report
Prototyping Path
Start Week | 2017-01-31: 2017-02-07
Week | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Starting | 2017-02-07 | 2017-02-14 | 2017-02-21 | 2017-02-28 | 2017-03-07 | 2017-03-14 | 2017-03-21 | 2017-03-28 | 2017-04-04 | 2017-04-11
Phase one | 2017-01-17: Basic Layout
Inital Drawings
Phase Two | 2017-02-07: Iteration #1 (Focus: Social networking)
Iteration #2 (Focus: Profile)
Iteration #3 (Focus: Competition)
Iteration #4 (Focus: Bud Fixes)
Iteration #5 (Focus: Functionality
Iteration #6 Complete
Documentation Path
Start Week | 2017-01-31: 2017-02-07
Week | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Starting | 2017-02-07 | 2017-02-14 | 2017-02-21 | 2017-02-28 | 2017-03-07 | 2017-03-14 | 2017-03-21 | 2017-03-28 | 2017-04-04
Phase one | 2017-01-17: Charter
Status Report #1
Timeline
Final Presentation Work
Phase Two | 2017-01-24: Status Report #2
Charter Update
Status Report #3
Competitor Data
Scope Document
Activity Cost
Risk Register
Stakeholder Register
Financial Data
Phase Three | 2017-03-14: Status Report #4
Final Charter
Final Presentation

## Month
Project Title | [22 empty] | Project Schedule
Project Schedule Template
|  | Start Date | 2014-01-01 | [19 empty] | © 2014 Vertex42 LLC
Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
| 2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-04-01 | 2014-05-01 | 2014-06-01 | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01 | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01 | Notes
| 2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-04-01 | 2014-05-01 | 2014-06-01 | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01 | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01
Phase
One
Phase
Two
Phase
Three

## Sample
Project Title | [18 empty] | Project Schedule
Project Schedule Template
|  | Start Week | 2014-01-05 | [15 empty] | © 2014 Vertex42 LLC
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Starting | 2014-01-05 | 2014-01-12 | 2014-01-19 | 2014-01-26 | 2014-02-02 | 2014-02-09 | 2014-02-16 | 2014-02-23 | 2014-03-02 | 2014-03-09 | 2014-03-16 | 2014-03-23 | 2014-03-30 | 2014-04-06 | 2014-04-13 | 2014-04-20 | 2014-04-27 | 2014-05-04 | 2014-05-11 | 2014-05-18 | Notes
| 2014-01-05 | 2014-01-12 | 2014-01-19 | 2014-01-26 | 2014-02-02 | 2014-02-09 | 2014-02-16 | 2014-02-23 | 2014-03-02 | 2014-03-09 | 2014-03-16 | 2014-03-23 | 2014-03-30 | 2014-04-06 | 2014-04-13 | 2014-04-20 | 2014-04-27 | 2014-05-04 | 2014-05-11 | 2014-05-18
Phase | 2014-01-05: Quality Assurance Plan; 2014-05-18: P R O J E C T E N D
One | 2014-01-12: Project Plan
Plan Review
Phase | 2014-01-26: Draft Requrements
Two | 2014-01-26: Capacity Planning
Project Test Plan
Acceptance Test Plan
Final Requirements Specifications
Phase Review and Approval
Phase | 2014-02-16: A d d i t i o n a l f u n d s; 2014-02-23: Draft Design Specifications
Three | 2014-02-23: Configuration Management Plan
Architectue Design Plan
Define Interface Requirements
Shared Component Design
Integration Test Plan
Define Project Guidelines
Final Design Specifications
Phase Review and Approval

## Help
HELP
http://www.vertex42.com/ExcelTemplates/project-schedule-template.html |  | © 2014 Vertex42 LLC
About this Template
This project schedule can be used to create a basic timeline for your project.
Try the Vertex42 Gantt Chart Template if you want to something more automated for creating and managing your project schedule. (See the reference below).
How to use this Template
1) | Enter your project start date in cell E3. This will automatically update the dates in rows 6 and 7.
2) | Add tasks: Choose what phase (row) and week (column) the task will start and enter the task title into that cell. Then fill in the background color of the cells to indicate how long the task will take to complete.
If you would like to show the completion status of a task, you can fill the background with a darker or different color (see the Sample worksheet for an example).
3) | Add a milestone: If you'd like to show a milestone, you can create a vertical "line" in the schedule by changing the cell borders and the background fill (see the Sample worksheet).
Note: In the sample worksheet, the milestones text is displayed vertically. You can do that by entering each character on a new line. Simply push "Ctrl+Enter" after typing each letter, then turn on text wrapping.
Additional Help
The link at the top of this worksheet will take you to the web page on vertex42.com that talks about this template.
REFERENCES
SEE ALSO | Vertex42.com: Gantt Chart Template
SEE ALSO | Vertex42.com: Project Management Templates
TIPS | Vertex42.com: Spreadsheet Tips Workbook

## ©
Project Schedule Template
By Vertex42.com
http://www.vertex42.com/ExcelTemplates/project-schedule-template.html
© 2014 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is considered a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
See License Agreement
http://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet. If necessary, you may hide it by right-clicking on the tab and selecting Hide.