## Sheet1
Risk Identification |  |  | Qualitative Rating |  |  |  | Risk Response
Risk ID | Risk | Risk Category | Probability | Impact | Risk Score | Risk Ranking | Risk Response | Trigger | Risk Owner
RR1 | Failure to Sell Prototype | Project | 25 | 100 | 2500 | 1 | Accept | The prototype is not what people want or there is no need for the project
RR2 | Not Completing the Prototype | Prototype | 20 | 100 | 2000 | 2 | Accept | The first completed iteratio of the prototype is not completed by April 25th
RR3 | Sponsor Leaving | Personale | 5 | 25 | 125 | 8 | Mitigate | Sponsor leaves the project beforethe completion
RR4 | Falling off Schedule | Scheduling | 15 | 25 | 375 | 7 | Mitigate | The workload is too heavy and the documents and prototype fall behind
RR5 | Spring Break | Scheduling | 100 | 5 | 500 | 6 | Mitigate | Students leave for Srping break and do not complete work
RR6 | Medical Emergency | Personale | 5 | 10 | 50 | 10 | Mitigate | Student has a medical emergency and cannot continue project
RR7 | Inadequate Team Member | Personale | 25 | 50 | 1250 | 3 | Mitigate | Team member does do the same amount of work as other students and the workload is distributed amoung members
RR8 | Members Missing Meetings | Personale | 50 | 25 | 1250 | 4 | Mitigate | Members fail to remember the meeting times and dates
RR9 | Cancelled Meetings | Scheduling | 15 | 50 | 750 | 5 | Mitigate | Meetings need to be cancelled or reschduled due to team members or work missing
RR10 | Scope Creep | Project | 25 | 5 | 125 | 9 | Mitigate | Scope is not well defined and team members creep away from actual scope