## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2017-02-16
Project Name: | WorkFit | [5 empty] | Project Status: | G
Project Description: | Organizations across the world are faced with unhealthy and unproductive employees more commonly than ever before. These lethargic workers, who cannot even touch their toes, lead to decreased productivity as well as increased depression. In order to address the balance of work and activity in the workplace we are proposing a new application for a healthier workplace. Utilizing geolocation and healthy goal suggestions, including foods and activities, employees will get a better idea of how healthy they are at work. This application will remind employees to move and eat well while also updating them on their our personal goals daily, weekly or monthly. There would need to be a buy in for the company to realize that if this application is used there would be a decrease in health insurance cost for the company and individuals. Features: - Personal daily, weekly,monthly goals - Geolocation tracking for workout goals (walking, running, etc.) - Recommend food options at nearby resturants based on user's nutrition preferences - Friend location tracking to meet up and network as well as get up and move - Point system which goes to rewards from the company - Compete across the company individually, in teams, or in business functions to get the most points and meet the most goals.
Customer | Companies who choose to utilize the application.
Project Core Team: | Jon Kerin, Thompson Nguyen, Sara Monahan, Matt Leaver
Next Milestone: | First Iteration of Prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 1/30/2017 - 4/30/2017 | Testing | R | 2017-03-28
Design | Y | 2/13/17- 4/30/2017 | Installation | R | 2017-04-30
Construction | Y | 2017-03-06
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
In the past two weeks we have been doing two seperate tracks. Jon and Sara have been doing research for the final project, focusing on the competition and cost/benefit analysis. Jon is researching credible ways to create revenue in order to substantiate the financial analysis and overall business plan. Thompson and Matt have been working closely with the prototype, focusing on the design and functionality of it. We also have decided that Sara will be the touch point between the project mentor and the team. The team also refinded the scope of the project and updated the project charter.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Planning Project | G | Design/Analysis |  | 2017-01-30 | 2017-01-30
Business Case (Research) | Y | Analysis |  | 2017-02-13 | 2017-02-13
Prototype Planning | Y | Planning |  | 2017-02-13 | 2017-02-13
Prototype Design | R | Design |  | 2017-03-01 | 2017-03-03
R
R
R
R
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Scope Creep |  | R | Scope Creep would occur with marketing the application to employees rather than corporations |  |  |  | All
Revenue Stream |  | Y | Research phase currently; potential parterning with MilkCrate/Yelp for additional revenue |  |  |  | All
JustinMInd |  | Y | Software issues regarding saving and usage of prior prototype |  |  |  | Matt and Thompson
Planned Accomplishments
A second iteration of the prototype with functionality; outline personnas in the prototype. A refined copy of the PowerPoint presentation supported with financial data especially. We also plan to keep refining and updating our charter. We have our first meeting on March 17th with our mentor; we plan to ask basic questions about the idea and how to refine our scope even further while getting ideas about potential revenue streams.