## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2017-01-30
Project Name: | WorkFit | [5 empty] | Project Status: | G
Project Description: | Info from project charter
Customer | Employers who choose to utilize the application as well as organizations
Project Core Team: | Jon Kerin, Thompson Nguyen, Sara Monahan, Matt Leaver
Next Milestone: | Detailed WBS
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 1/30/2017 - 4/30/2017 | Testing | G | 2017-03-28
Design | G | 1/30/2017 - 4/30/2017 | Installation | G | 2017-04-30
Construction | G | 2017-03-01
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Last week, we had our first group meeting. We were able to brainstorm a plan and supplementary ideas for the implementation of the application. We were able to think of unconventional revenue streams and focus on who would utilize our application. We have decided to use JustinMind as our prototyping tool due to our past experience with the technology. Matt, Thompson, Sara, and Jon are all comfortable with navigating and using JustinMind to develop a working prototype.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Planning Project | G | Design/Analysis |  | 2017-01-30 | 2017-01-30
Y
G
G
G
G
G
G
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Not Available |  | G | Not Available at this time |  |  |  | Project Team
Scope Creep |  | Y | Scope Creep would occur with marketing the application to employees rather than corporations
Planned Accomplishments