## Sheet1
Risk Register
Risk Number | Risk Description | Risk Strategy & response Response (4 choices: Mitigate, Transfer, Avoid, Accept) |  | Probability | Impact | Risk Score | Priority | Risk Owner | Status
ID1 | Someone gaining unauthorised access and locks/deletes important documents. | Mitigate | Have adequate cybersecurity protocols in place | Low | High | 3 | 2 | MK
ID2 | An employee may leak confidential documents to competitors. | Mitigate | Propose consequences to employees that break NDA | Low | High | 3 | 1 | LP
ID3 | Key employee is unable to work due to injury | Accept | Pay worker's compensation. | Moderate | Moderate | 4 | 4 | LP
ID4 | Fire, flood, theft any threat what would physically damage IT devices | Transfer | Have insurance coverage to pay for damages | Moderate | Moderate | 4 | 3 | MK
ID5 | IT personnel not skilled enough | Mitigate | Ensure cross training between key employees and new hires. | Low | Moderate | 2 | 6 | AL
ID6 | Leakage of customer data from someone internal or extrenal. | Mitigate | Have adequate cybersecurity protocols in place | Low | High | 3 | 5 | MK
ID7 | Servers go down as a result of a crash or system failure. | Mitigate | Have a backup servers. | Low | Moderate | 2 | 7 | AL
LEGEND
Probability | Impact
Low | Low | 1
Moderate | Moderate | 2
High | High | 3