## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2017-11-06
Project Name: | TUStudy | [5 empty] | Project Status: | Y
Project Description: | An easy-to-use app for students to locate and utilize available computers, breakout rooms, writing & tutorial appointments at Temple University.
Customer | Temple University
Project Core Team: | Project Manager: BS Srinath Amruth Business Analyst: Glenn Diener Solutions Engineer: Jacky Wong
Next Milestone: | Delivery of Testing plan
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2017-11-06 | Testing | R | 2017-11-06
Design | Y | 2017-11-06
Construction | Y | 2017-11-06
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Last week we came together and talked about the design of the project and how we should divide up the work in JustInMind. The layout/GUI is still a work in progress. Other considerations soon are surveys to be conducted for more feedback, retrieving necessary data for the project from IT Department/ Project Mentor.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Test plan | G | Design |  | 2017-10-17 |  |  | 2017-11-07
Final project plan | Y | Analysis |  | 2017-11-30 |  |  | 2017-11-28
UI Mockup | Y | Design
--- User login | Y | Design |  | 2017-10-24 | 2017-10-24 |  | 2017-10-27
--- Computer Database | Y | Design |  | 2017-10-27 |  |  | 2017-10-30
--- Location Settings | Y | Design |  | 2017-10-30 |  |  | 2017-10-31
--- Reservation Backout | Y | Design |  | 2017-10-31 |  |  | 2017-11-03
--- Reservation Menu | Y | Design |  | 2017-10-31 |  |  | 2017-11-03
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Planned Accomplishments
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.