## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2017-11-06
Project Name: | TUStudy | [5 empty] | Project Status: | Y | G | Good/Completed
Project Description: | An easy-to-use app for students to locate and utilize available computers, breakout rooms, writing & tutorial appointments at Temple University. | [7 empty] | Y | Ongoing/Under work
[9 empty] | R | Yet to be started/initiated
Customer | Temple University
Project Core Team: | Project Manager: BS Srinath Amruth Business Analyst: Glenn Diener Solutions Engineer: Jacky Wong
Next Milestone: | Delivery of Testing plan
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2017-11-06 | Testing | R | 2017-11-06
Design | Y | 2017-11-06
Construction | Y | 2017-11-06
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Last week we came together and talked about the design of the project and how we should divide up the work in JustInMind. The layout/GUI is still a work in progress. Other considerations soon are surveys to be conducted for more feedback, retrieving necessary data for the project from IT Department/ Project Mentor.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Test plan | Y | Design |  | 24th Oct
Final project plan | Y | Analysis |  | 24th Oct
UI Mockup | Y | Design |  | 24th Oct
--- User login | G | Design |  | 24th Oct |  |  | 14th Nov
--- Sidebar Menu | Y | Design |  | 24th Oct
--- Reservation Confirmation | Y | Design |  | 24th Oct
--- Reservation Menu | G | Design |  | 24th Oct |  |  | 14th Nov
--- Room Res landing page | Y | Design |  | 24th Oct
--- Tutor Res landing page | Y | Design |  | 24th Oct
--- Writing Asst Res landing page | Y | Design |  | 24th Oct
--- Computer Res landing page | Y | Design |  | 24th Oct
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Time period of Reservation |  | G | To consult with Tech Director of Tech Center - To be 1 hour for adequate time |  |  |  | Amruth
Allowing only 1 reservation at a time |  | Y | Algorithm to be research and implemented |  |  |  | Jacky
Planned Accomplishments
1. The front facing page of the app has been constructed. 2. Resource options have been stated out in the following page.
Note on B48: Key Issues are issues that need your CM Director-level understanding and awareness.